# Town of Pamplin City Resilience Plan Application

Scope of Work Narrative

CFPF Round 5

Table of Contents

Introduction	2

Review of Needs & Problems	2

Goals and Objectives	5

Assessment of Capacity & Planning Financial, Human, Technical Assistance, and Training	6

Work Plan	7

Evaluation	12

Town of Pamplin City

Community Flood Preparedness Fund & Resilient Virginia Revolving Loan Fund

Scope of Work

Period of Performance: May 2025 through November 2025

Submission Date: January X, 2025

## Introduction

Pamplin City is a small town located both in Appomattox and Prince Edward counties. The Town serves as a vital service hub for surrounding rural areas since it straddles U.S. Route 460. The town is notable for being the western terminus of the High Bridge Trail State Park, a 30-mile linear park ideal for hiking and biking, featuring the impressive High Bridge over the Appomattox River. Pamplin City has a rich historical background, and it was the home of the Pamplin Smoking Pipe Manufacturing Company which at one point was the largest factory of its kind. Additionally, the Town office is housed in a restored railroad depot that reflects the Town’s heritage as a transportation hub in the late 19th century.

The Town will seek a consultant to support the creation of a town-wide resilience plan focused on flooding and natural resource protection. The Resilience Plan will result in a guiding document for community flood resilience through vision and goals setting, creation of a risk matrix using best available data, collection of community data through meaningful public participation, and prioritization of actions and mitigation strategies. Although the Resilience Plan will have a strong focus on flooding, as the town’s location in a floodplain makes it a critical hazard, the plan will also address other hazards the Town faces. Impacts from multiple hazards, including those that may cause, influence, or result from flooding events, as well as those that can impact the transportation network will be assessed.

Figure 1: Town of Pamplin City, Virginia

## Review of Needs & Problems

The creation of a town-wide resilience plan will consolidate and reflect upon the Town’s resiliency goals. The following narrative responds to the prompts in the 2024 Funding Manual for the Virginia Community Flood Preparedness Fund Round 5.

Need

- Specific problem being solved (not just that flooding exists or may occur in the future)

  - It is project based with a focus on flood control & resilience

    - The Resilience Plan will focus on the creation and prioritization of projects that mitigate flooding and enhance community resilience to flooding.

  - It incorporates nature-based infrastructure to the maximum extent possible

    - Consideration of resiliency actions that impact the Town’s environmental assets will be included in the discussions of priority and mitigation actions.

  - It includes all parts of a community regardless of socioeconomics or race, and addresses flood resilience needs of underserved populations

    - All residents, regardless of location, socioeconomics, or race will be included in the risk and vulnerability assessment, engagement process, and overall resilience plan for the Town of Pamplin City. Underserved populations will be included and emphasized in the prioritization criteria for resilience activities.

  - It identifies flooding issues in all areas of the community, not just SFHAs, and addresses repetitive loss properties

    - The resilience plan will assess flooding impacts from all types of flooding in all areas of the Town, not just within the Special Flood Hazard Areas (SFHAs).

  - If property acquisitions are included, must also include equitable relocation strategies (if applicable)

    - Property acquisitions will be determined thorough the resilience plan process. If they are discussed, equitable relocation strategies will be included.

  - It includes a strategy for debris management in water channels and floodplains

    - The Town will include a strategy for debris management in water channels and floodplains in the plan.

  - It includes administrative procedures for substantial damage / improvement of structures within the SFHA

    - The Town’s existing administrative procedures for substantial damage/improvement of structures within the SFHA will be included in the plan.

  - It includes coordination with other local and inter-jurisdictional plans and projects and has a timeline for implementation

    - The Resilience Plan will incorporate findings from the Central Virginia Planning District Hazard Mitigation Plan and the Town’s Comprehensive Plan. Along with goals and objectives identified in these plans and additional strategies identified from this proposed process, a timeline for implementation will be included with the plan.

  - It is based on the best available science and incorporates climate change, sea level rise, storm surge (where appropriate) and current flood maps

    - The Resilience Plan will be based on the best available science as required.

- Factors which contribute to the identified problem.

Flooding in Pamplin City typically occurs during heavy rainfall associated with tropical storms and hurricanes. Flash flooding in Pamplin can cause significant damage to residents and businesses. For example, a home outside of, but near the Town limits, collapsed into its basement during Tropical Storm Debby in August of 2024. Flooding often occurs in the Town’s downtown area due to inadequate stormwater drainage, which affects residents and businesses. Half of the Town of Pamplin City is not connected to a municipal sewer system, requiring the use of septic tanks. This can pose a public health hazard during severe flooding events.

- Why the project is needed either locally or regionally.

The Town of Pamplin City will continue to experience severe flooding events that threaten the town’s infrastructure and residents as climate change increases the frequency of extreme weather events such as tropical storms. A centralized and project-based planning effort will enhance the town’s ability to make informed and equitable decisions to increase community resilience.

- How the project decreases the risk to public safety through flood risk reduction.

The creation of a resilience plan reduces the risk to public safety by creating a plan to reduce flood impacts and increasing community awareness about flooding during the process.

- How the project protects or conserves natural resources.

The Town of Pamplin City takes great pride in its natural resources. Its natural resources and close proximity to the Appomattox River attracts tourists from all over. Therefore, the Resilience Plan will assess the Town’s natural resources and prioritize actions that preserve and protect the Town’s existing natural resources.

- Who is protected.

This plan will cover the residents, workers, and tourists who visit the Town of Pamplin City.

- The safety threats, or environmental concerns related to flood risk.

The safety of Pamplin City residents is threatened by flooding. As seen in the recent flooding from Tropical Storm Debby, flash fooding can cause severe damage to homes, increasing the vulnerability of already vulnerable populations. The use of septic tanks by half of the town poses both environmental and public safety concerns during severe flooding events.

- Groups to be targeted who might directly benefit from this flood risk reduction effort.

Even though the Resilience Plan will cover the entire town, areas that are at the highest risk for flooding will be prioritized as well as areas with underserved populations.

- What would happen (or not happen) if the applicant does not receive funding.

If the town does not receive funding for this plan, it is likely that development of a town-wide resilience plan will not be undertaken. Resilience planning is an expensive process and with few staff, there will not be an opportunity to pursue a plan at this scale. As a result, high risk areas will continue to experience flooding and damage. The funding provided for this resilience plan will allow the community to pursue funding for flood resilience projects generated through this plan in later rounds of CFPF.

## Goals and Objectives

Pamplin City has established the following Goals and Objectives for the planning process.

| Table 2: Goals and Objectives |  |  |
| --- | --- | --- |
| Goal | Objective | Objective Measure of Success |
| Goal 1: Develop and Adopt a Resilience Plan for the Town of Pamplin City | Objective 1.1: Develop a Resilience Plan that Meets DCR Requirements Objective 1.2: Collaborate with local, state, and regional entities to ensure plan alignment with existing initiatives | Objective Measure of Success 1.1.1: Town Council approval and formal adoption of the Flood Resilience Plan Objective Measure of Success 1.2.1: Documentation of meetings and partnerships with relevant stakeholders, including the Department of Conservation and Recreation |
| Goal 2: Enhance Community Preparedness for Flooding | Objective 2.1: Identify repetitive loss or potential repetitive loss properties to assist property owners in making informed mitigation decisions | Objective Measure of Success 2.1.1: Documentation of repetitive loss risks and actions provided with mitigation options and resources to reduce future losses. |
| Goal 3: Identify Future Potential Resilience Projects | Objective 3.1: Develop risk matrix to identify current and future potential vulnerabilities Objective 3.2: Identify grant funding opportunities to support future resilience projects. | Objective Measure of Success 3.1.1: Prioritized list of vulnerabilities and actions Objective Measure of Success 3.2.1: At least one funding source identified for high priority projects |

## Assessment of Capacity & Planning Financial, Human, Technical Assistance, and Training

Pamplin City recognizes the essential steps in the Resilience Plan development process and is committed to conducting a thorough assessment to support implementable and fundable resilience projects, as such the Town requests assistance from the Community Flood Preparedness Fund to fund consultant services to support development of the new Resilience Plan.

As part of our Resilience Plan development approach, the Town has included the following considerations to support grant management:

- Resource Development Strategies: Other funding opportunities, such as available State grant programs, will be explored by the Town.

- Staff Capabilities and Training: To improve the capabilities and resourcefulness of this plan, the Town plans on contracting consultants to lead the process and develop the plan document. Existing staff will be included in this process and those located in specific roles and/or departments will be informed of their roles in implementing strategies.

- Policy Management and Development: Plan alignment is essential to building and amplifying resilience efforts across the Town, Region, and Commonwealth. The Resilience Plan development is expected to support coordination across existing activities, plans, and policies while leading to resilience project recommendations. These recommendations, developed through the planning process, may include structural and nonstructural solutions, including local policies to support resilience. To promote alignment with the Resilience Plan and existing policies, plans, and activities, the Town will provide opportunities to engage with the localities within Appomattox County and the Central Virginia Planning District Commission, engage with relevant regional and state agencies, and review existing efforts in the planning effort.

- Stakeholder Identification and Outreach: Stakeholder identification and outreach is a vital part of this approach. The team will host a guided workshop with stakeholders to identify key inputs for plan development. The process for this content development includes following the Community Resilience Building (CRB) process, which is a comprehensive, community-driven approach to enhancing resilience against various hazards and challenges. This process facilitates rich dialogue and information sharing among participants, enabling them to collaboratively develop strategies that address both immediate and long-term resilience needs. By engaging community members from the outset, the CRB process ensures that resilience goals and priorities are feasible, realistic, and tailored to the specific context of each community. The resulting plan will be publicly available in an accessible format to share with stakeholders.

## Work Plan

- What are the major activities and tasks.

  - Please see Tasks 1-7 below

- Who is responsible for completing the activities and tasks.

  - The Town Lead will lead the plan development with consultant support

- What is the timeframe for accomplishing activities and tasks.

  - The planning process is seven months. Please see the schedule section for a breakdown of tasks.

- Identify the required partners to ensure success and where they are represented in the workplan.

  - Partners are vital to ensure the success of this resilience plan. There is a summary of the partners and their roles at the end of the work plan.

- Deliverables

  - A Resilience Plan

  - Scope of work for priority project for future CFPF funding

- Maintenance plan tied to the identified viability of the project. Plan for sustaining the project after the agreement period (if applicable).

  - Please see Task 5

#### PROJECT TASKS

##### TASK 1: PROJECT INITIATION & MANAGEMENT

Pamplin City will develop a Resilience Plan to reflect current priorities and goals of DCR and the Town. The project will be led by Town staff. The project is expected to take 7 months, which is outlined in the Schedule. Below represents the major tasks and activities.

#### Task 1.1 Form the Core Team and Project Team

The Core Team will include the Mayor, consultant, and other key members as determined necessary to guide and progress the plan.

The Project Team will be primarily comprised of representatives from the Town Administration. These representatives are currently engaged in flood management and resilience activities. Additional participants, such as the regional PDC (Central Virginia PDC) or the Economic Development Authority, will also be considered for the Project Team, as determined by the Core Team.

Project Team members will meet regularly and will be responsible for providing input throughout the planning process such as understanding of existing and planned projects, issues, plans, data, as well as review of draft materials.

#### Task 1.2 Project Management

The project will begin with a Core Team Project Initiation Meeting to review scope, schedule, goals, and kickoff coordination. Throughout the project, the Core Team will meet regularly (approximately bi-weekly).

The planning lead will also be responsible for quarterly reporting.

##### TASK 2: RESILIENCE ACTIVITY REVIEW

#### Task 2.1 Existing Conditions Documentation

The project team will review local regulations and planning tools that pertain to climate resilience, including but not limited to, the Central Virginia Planning District Commission’s Mitigation Plan, Floodplain Ordinance, and the Comprehensive Plan. Throughout the review and development of a crosswalk, the consultant project team will document success stories, areas of growth/opportunities for action, data needs, and actions that have already been identified as priorities that coincide with climate resilience. The project team will also work with municipal leaders to collect and analyze data on infrastructure, population, and natural resources vulnerabilities to flooding, as well as additional natural hazards. Key assets and community features such as schools, bridges, and natural resources will also be mapped for the use in community workshops. The project team will also develop other maps using publicly available data to geospatially reference assets for conversations with stakeholders.

As part of the baseline assessment, the project team will interview selected members of the Core Team and other key stakeholders to collect various perspectives and detailed information on critical areas of the plan. Interviews will be conducted as necessary to prepare for the workshop or to further develop the results of the workshop.

#### Task 2.2 Vision and Goals Setting

The consultant project team will work with the Town and Core Team to develop a vision, set goals for the CFPF program and a set of core principles. The core principles will drive decisions throughout the plan and will be incorporated into the Action Prioritization Matrix. The goals will draw upon the planning and policy crosswalk in addition to leading best practices through Virginia and the nation. The Core Team will have an opportunity to react, amend, and add goals during a bi-weekly meeting.

##### TASK 3: COMMUNITY RESILIENCE BUILDING WORKSHOP

During this task, the project team will host a guided workshop with stakeholders to identify key inputs for plan development. The process for this content development includes following the Community Resilience Building (CRB) process, which is a comprehensive, community-driven approach to enhancing resilience against various hazards and challenges. This "anywhere at any scale" methodology brings together diverse stakeholders to identify top hazards, assess current strengths and vulnerabilities, and prioritize actions to improve community resilience and has been used in many communities throughout the county to facilitate the development of a resilience plan. The CRB Workshop, a key component of this process, facilitates rich dialogue and information sharing among participants, enabling them to collaboratively develop strategies that address both immediate and long-term resilience needs. By engaging community members from the outset, the CRB process ensures that resilience goals and priorities are feasible, realistic, and tailored to the specific context of each community. This approach not only builds and strengthens social capital but also fosters a sense of ownership and commitment to implementing resilience measures, ultimately leading to more sustainable and effective outcomes.

#### Task 3.1 Create Workshop Material

The project team will prepare for the Town’s one full-day or two half-day CRB workshop(s), using the Community Resilience Building workshop guide developed by The Nature Conservancy. They will:

- Develop the agenda and materials for the workshop(s), including maps of key assets and community features such as schools, bridges, and natural resources for use by the workshop participants.

- Incorporate the best available natural hazard data and other relevant information into the workshop materials to enhance participants’ understanding of flooding.

- Work with the Core Team to facilitate workshop groupings (such as sector, geography, roles and responsibilities, and experience), dividing the 20 to 40 participants among five to six groups for smaller table discussions.

- Risk matrices, as described within the CRB Building webpage (www. communityresiliencebuilding.com).

They will also support the Core Team in identifying and inviting stakeholders to participate in the workshop(s); these people will include local leaders representing municipal, state and federal government; businesses; institutions; and not-for-profit organizations.

#### Task 3.2 Conduct the Workshop

The consultant team will conduct the CRB Workshop(s) to characterize the Town’s hazards, vulnerabilities, and strengths related to the infrastructure, societal, and environmental assets. They will:

- Understand connections between ongoing community issues, hazards, and local planning and actions in the municipalities.

- Identify and map vulnerabilities and strengths to develop infrastructure, societal, and natural resource risk profiles for the municipalities.

- Develop and prioritize actions and clearly delineated next steps for the municipalities, local organizations, businesses, private citizens, neighborhoods, and community groups.

- Identify areas for debris management

- Identify opportunities to advance actions that further reduce the impact of hazards and increase resilience across and within municipalities.

##### TASK 4: DEVELOP ACTIONS FOR FLOOD PREPAREDNESS

#### Task 4.1 Develop a Risk Matrix

The consultant team will work with the Core Team to synthesize the workshop(s) participants’ input and prepare a master Risk Matrix summarizing the Risk Matrices prepared at each workshop table. This will be the foundation for the development of actions to reduce risks to flooding in the community.

#### Task 4.2 Develop Priority Actions and Mitigation Strategies

As an outcome of developing the Risk Matrix, the project team will work with the Core Team and local officials to identify resilience-building actions that address potential risks to community’s assets of infrastructure, society, and environment. These actions will include the several highest Priority Actions that would mitigate the flooding vulnerabilities. They will assist in conceptualizing projects that are ready for implementation, will most significantly improve resiliency and flooding preparedness, and support the improvement of capabilities and capacity. They will help to shape the project actions to address potential be received favorably by DCR during the next round of CFPF funding. In a strategic planning meeting, the project team will work to further develop potential projects and to develop a strategy for obtaining funding source(s) for those projects.

#### Task 4.3 Action Prioritization

Using the Action Prioritization Matrix, the project team will work with the Core Team to identify high priority resilience-building actions that address principal vulnerabilities within the community’s infrastructure, societal, and environmental assets and that will help meet the goals established at the beginning of the planning process. Actions that are identified as high priorities will undergo further analysis to identify items such as cost and feasibility. They will further assist in refining actions to develop specific implementation strategies, which may include identifying next steps and funding sources.

##### TASK 5: DEVELOP THE PLAN

#### Task 5.1 Summarize Findings

Characterizing current and projected hazard impacts within the Town provides a critical foundation for developing hazard mitigation strategies. The resilience plan will assess flooding impacts in all areas of the Town, not just within the Special Flood Hazard Areas (SFHAs). Impacts from multiple hazards, including those that may cause, influence, or result from flooding events, as well as those that can impact the transportation network will be assessed.

Results of the CRB process will serve as an exposure, risk, and vulnerability assessment and will be summarized using maps, figures, and narrative for presentation in the resilience plan. This will include the following key summaries:

- High flood risk areas with supporting maps

- Critical facilities with high flood exposure

- Underserved communities with high flood exposure

- Strategy for debris management

- Natural infrastructure with high flood exposure

A GIS database that compiles data used in the analysis will also be developed.

#### Task 5.2 Implementation Plan

The implementation plan will be crafted to foster accountability and track progress on high-priority actions. Each action will be comprehensively detailed with specific attributes, including a clear description, implementation timeline (with phasing if required), lead department and staff, supporting departments and partners, estimated costs, anticipated benefits, flood hazards mitigated, potential funding sources, and any additional hazards addressed. Furthermore, the highest priority projects will feasibility assessments and actionable steps towards completion. This enhanced focus on the most critical projects aims to equip the Town with a targeted, actionable strategy, ensuring efficient resource allocation and maximizing impact on flood mitigation and overall hazard reduction.

#### Task 5.3 Plan Maintenance Procedure

The implementation of the plan will be further supported by carefully designed maintenance procedures. These procedures will encompass a systematic approach to reviewing project progress and will establish protocols for keeping both the Project Team and stakeholders regularly informed about the plan's advancement, potentially on a semi-annual basis. The Project Team will be responsible for developing and approving these procedures, ensuring a cohesive and well-structured approach to plan maintenance.

##### TASK 6: FINAL PLAN

#### Task 6.1 Draft Plan

The project team will compile a draft plan, integrating the findings from the CRB process and the proposed resilience strategies. This draft report will serve as a foundation for further review and refinement before finalizing the plan. The plan will also include map products and a summary of future strategies and projects along with an implementation timeline, responsible agencies and potential partnerships, and anticipated funding sources. The draft plan will first be reviewed by the project team. This includes review by a Certified Floodplain Manager. The plan will be edited based on project team and the CFM comments, allowing for CFM endorsement of the plan.

#### Task 6.2 Final Plan and Presentation Materials

Following any necessary edits, the plan will be posted digitally and advertised for public and stakeholder review for approximately 3 weeks. Once all comments have been addressed from the project team, the team will work with the Town to post a draft plan on the Town website or provide a link to it. The Town will create a digitally accessible Final Plan for posting to the Town’s website. The plan will also be summarized into digestible, plain language materials such as a digital placemat and/or GIS Story Map.

#### Task 6.3 Plan Review and Adoption

Once the project team and public input has been received and incorporated, the plan will be submitted for DCR Review and approval.

##### TASK 7: COMMUNITY IMPLEMENTATION

#### Task 7.1 Priority Project Scope

The project team will develop a detailed scope and collect necessary information for a priority project to apply for future funding through the CFPF program. This could include a scope for an additional study needed to inform decision-making or funding for the design of a nature-based or infrastructure project.

#### Task 7.2 Resident Flooding Preparedness Toolkit

The project team will develop a resident flooding preparedness toolkit to encompass a wide range of essential information and resources to help community members effectively prepare for, respond to, and recover from flood events. The toolkit will include sections on understanding flood risks, creating emergency plans, assembling disaster supply kits, and implementing home mitigation strategies. The toolkit will also incorporate communication templates, including social media strategies and public meeting guides, to facilitate effective information dissemination. Additionally, it will offer practical checklists, contact information for local authorities, and resources for post-flood recovery. By addressing these key areas, the toolkit will empower residents to take proactive steps in safeguarding their families, homes, and communities against flood-related hazards.

#### PARTNERS FOR SUCCESS

#### Key partners for success on a resilience plan in Pamplin City, VA would include local government officials, planning district commissions, and state agencies focused on environment, energy, and emergency management. Given Pamplin City's high poverty rate and recent wastewater treatment plant improvements, organizations like SERCAP (Southeast Rural Community Assistance Project) would be crucial partners for addressing infrastructure needs

#### SCHEDULE

The plan will be completed over a seven-month planning process. The Town proposes to commence the planning process in March 2025.

| Task # | Task Name | May-25 | Jun-25 | Jul-25 | Aug-25 | Sept-25 | Oct-25 | Nov-25 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task 1 | Project Initiation & Management |  |  |  |  |  |  |  |
| Task 2 | Resilience Activity Review |  |  |  |  |  |  |  |
| Task 3 | Community Resilience Building Workshop |  |  |  |  |  |  |  |
| Task 4 | Develop Actions For Flood Preparedness |  |  |  |  |  |  |  |
| Task 5 | Develop The Plan |  |  |  |  |  |  |  |
| Task 6 | Final Plan |  |  |  |  |  |  |  |

## Evaluation

- Indicators of success.

The following indicates measures of success for the Pamplin City Resilience Plan.

| Table 3. Measures of Success |  |
| --- | --- |
| Performance Output | Measurement |
| Actionable Plan | DCR-approved and Town-adopted. |
| Coordinated Resilience Activities | Defined mechanisms to promote multi-department coordination to increase efficiencies and risk reduction. |
| Prioritized Projects | Wide range of flood reduction project types identified (e.g., planning, policy, structural and natural and nature-based) and connected to funding sources. |
| Plan Maintenance Procedures | Procedures agreed upon by the Project Team to support regular meetings of the Project Team, project status reviews, public updates, and a plan update process. |

- Data that will be collected and how the data will be used to measure success.

Action progress will be captured in an Excel tracker by the responsible parties. Success will be measured via activity completion, which will begin with plan development, approval, and adoption.

- How was cost effectiveness evaluated and measured against the expected outcomes?

The Town considered the cost of developing a plan compared to the potential issues of continuing on without one. Without a plan in place, the Town loses efficiencies by:

- Not having a mechanism for coordination and tracking resilience projects;

- Potential for implementing projects that may result in a reactive, “band-aid” approach;

- Undertaking multiple risk assessments that serve a similar purpose; and

- Not having an understanding of resilience needs and priorities to pursue in a strategic manner.

While specific dollars were not quantified, these examples demonstrate that resources would be lost to quickly exceed the value of the plan. As such, the plan was determined to be cost effective.

- What products, services, meetings, outreach efforts etc. will be conducted and how will success be measured?

The following table represents the efforts that will be conducted and performance measures.

| Table 4. Efforts Conducted and Performance Measures |  |  |  |
| --- | --- | --- | --- |
|  | Activity | # | Performance Measure |
| Planning Products | Visual and accessible planning document | 1 | Increase in county coordination and resilience strategy implementation |
|  | Risk Matrix development | 1 | Identification of vulnerable assets to a variety of hazards with actions identified to address vulnerability |
|  | Resilience Strategy Action Tracker | 1 | Increase in resilience strategy coordination |
| Outreach and Communication Efforts | Surveys | 2 | Insights into county and community resilience needs and opportunities and input on action and implementation |
|  | County/community workshop | Up to 2 half day or 1 full day | Insights into vulnerabilities and resilience capabilities |

- Project progress monitoring plan to ensure project meets the requirements of the agreement and is delivered on time. Outline how delays or other findings may be used to modify or improve outcomes/deliverables.

Throughout the project duration, the Town lead and consulting team will monitor the development of the plan to ensure timely completion and submission of deliverables. The planning process will take seven months. If delays occur, they will be explained in the quarterly report(s), as appropriate.

## Supporting Documentation

- Social Vulnerability Index Map

- Appomattox County Comprehensive Plan (2021 Update)

- Central Virginia Planning District Hazard Mitigation Plan 2020- Please use this link to access: https://www.cvhmp.com/static/pdf-viewer/web/viewer.html?file=/static/files/Central-Virginia-Planning-District-Hazard-Mitigation-Plan-2020.pdf

“Town of Pamplin | Appomattox County, VA,” accessed December 5, 2024, https://www.appomattoxcountyva.gov/291/Town-of-Pamplin.

“Town of Pamplin | Appomattox County, VA.”

“History | Appomattox County, VA,” accessed December 5, 2024, https://www.appomattoxcountyva.gov/288/History.

“Town of Pamplin | Appomattox County, VA.”

Virginia Department of Conservation and Recreation. Community Flood Preparedness Fund Round 5 Manual. Richmond, VA: Virginia Department of Conservation and Recreation, 2024. https://www.dcr.virginia.gov/dam-safety-and-floodplains/document/Round-5-CFPF-Manual.pdf.

Brittany Slaughter, “Pamplin Home Collapses into Basement after Tropical Depression Debby Rainfall,” WSET, August 9, 2024, https://wset.com/news/local/pamplin-home-collapses-into-basement-after-tropical-depression-debby-rainfall-hurricane-flooding-damage-august-2024.